## Sheet1
Crib Assembly
Activity | duration (hrs) | precedence | start time | end time | Comments
1.Add mattress to base | 0.25 | 17-20 | 3 | 3.25
2.Assemble baby mobile | 1 | start | 0 | 1 | What if we need a specialist for this, who is only available on Sundays?
3.Assemble base | 2 | start | 0 | 2
4.Assemble leg 1 | 0.5 | start | 0 | 0.5
5.Assemble leg 2 | 0.5 | start | 0 | 0.5
6.Assemble leg 3 | 0.5 | start | 0 | 0.5
7.Assemble leg 4 | 0.5 | start | 0 | 0.5
8.Assemble wall 1 | 1 | start | 0 | 1
9.Assemble wall 2 | 1.5 | start | 0 | 1.5
10.Assemble wall 3 | 1 | start | 0 | 1
11.Assemble wall 4 | 1.5 | start | 0 | 1.5
12.Attach baby mobile to walls 1-4 | 0.25 | 1 | 3.25 | 3.5 | The earliest we can finish is in 3.5 hours
13.Attach leg 1 to base | 0.25 | 3,4 | 2 | 2.25
14.Attach leg 2 to base | 0.5 | 3,5 | 2 | 2.5
15.Attach leg 3 to base | 0.25 | 3,6 | 2 | 2.25
16.Attach leg 4 to base | 0.5 | 3,7 | 2 | 2.5
17.Attach wall 1 to base | 0.5 | 3,8 | 2 | 2.5
18.Attach wall 2 to base | 1 | 3,9 | 2 | 3
19.Attach wall 3 to base | 0.5 | 3,10 | 2 | 2.5
20.Attach wall 4 to base | 1 | 3,11 | 2 | 3