## Sheet1
Crib Assembly
Assumption: only 4 people can work on this project
Activity | duration (hrs) | precedence | start time | end time | Comments
1.Add mattress to base | 0.25 | 17-20 | 4.75 | 5
2.Assemble baby mobile | 1 | start | 1.5 | 2.5 | What if we need a specialist for this, who is only available on Sundays?
3.Assemble base | 2 | start | 1.5 | 3.5 | We assume 8 people are available to work on this crib!!
4.Assemble leg 1 | 0.5 | start | 0 | 0.5
5.Assemble leg 2 | 0.5 | start | 0 | 0.5
6.Assemble leg 3 | 0.5 | start | 0 | 0.5
7.Assemble leg 4 | 0.5 | start | 0 | 0.5
8.Assemble wall 1 | 1 | start | 0.5 | 1.5
9.Assemble wall 2 | 1.5 | start | 0.5 | 2
10.Assemble wall 3 | 1 | start | 0.5 | 1.5
11.Assemble wall 4 | 1.5 | start | 0.5 | 2
12.Attach baby mobile to walls 1-4 | 0.25 | 1 | 5 | 5.25 | The earliest we can finish is in 5.25 hours
13.Attach leg 1 to base | 0.25 | 3,4 | 3.5 | 3.75
14.Attach leg 2 to base | 0.5 | 3,5 | 3.5 | 4
15.Attach leg 3 to base | 0.25 | 3,6 | 3.5 | 3.75
16.Attach leg 4 to base | 0.5 | 3,7 | 3.5 | 4
17.Attach wall 1 to base | 0.5 | 3,8 | 4 | 4.5
18.Attach wall 2 to base | 1 | 3,9 | 3.75 | 4.75
19.Attach wall 3 to base | 0.5 | 3,10 | 4 | 4.5
20.Attach wall 4 to base | 1 | 3,11 | 3.75 | 4.75
NOTE: we could have one person assemble wall 1 and 2, another person assemble 3 and 4, then one person do the base and one leg, one person do the baby mobile and 3 legs, then they will all finish after 2.5